## User Stories
User Stories
Theme | Priority | As the... | I want to be able to... | so I can...
Backend | High | User | have equal priority initially | play my music without having to wait a long time
Backend | High | Developer | priority is given to those who have joined session more recently | allow everyone to play at least one song
Frontend | High | User | have a visually simple interface | lear how to use it faster
UI | High | User | join any active session using a corresponding QR code | join the session easier
UI | High | User | add any available song from YouTube to the playlist | have more than one song on the playlist
UI | High | Host/Manager | reorder the playlist | manage the playlist
UI | High | Host | create/end a session | have a private queue
UI | High | Host | ban current users in session | remove users from the session
UI | High | User | see the full playlist | know the song that are in the queue
UI | High | User | retract actions done | undo undesired changes
User Account | High | User | user can create, use an account | keep track of their favorites and account information
Frontend | Med | User | see and play song and music at the same time | add my decals and have the app show me my available lots
UI | Med | User | add any song from another websites | have more options
UI | Med | Host | skip a song | keep the party mood up
UI | Med | Host | delete a song | remove unwanted songs
UI | Med | User | keep selection in queue | listen to the music I added without being in the session
UI | Med | User | add unlimited amount of songs | play music for long events
UI | Med | User | delete or pushed forward within playlist by vote | hear the songs that most of the people like
User Account | Med | User | store favorites | quickly pull up a specific playlist
Note on V1: User stories provide a high-level overview of product requirements.

## Sprint 1 Backlog
Sprint 1 Backlog | [5 empty] | Date | 3/14 - 3/20 |  |  | 3/21 - 3/27 |  |  | 3/28 - 4/3
Backlog Item | Pts. | Priority | Owner | Status | Remarks | Day: | W | F | M | W | F | M | W | F | M
Create simple bootstrap template | 4 | High | All-Team | not-started
Set Up Cloudforge | 4 | High | All-Team | not-started
Create simple nodejs server | 8 | High | Michael | not-started
Database | 16 | High | All-Team | not-started
Return value from database to front-end | 4 | High | All-Team | not-started
Install MySQL Server | 2 | Medium | All-Team | not-started
Research on node.js | 16 | Medium | All-Team | not-started
Refine User Interface Design | 8 | Medium | All-Team | not-started
Research YouTube API | 16 | Medium | All-Team | not-started
Note on B2: Based on complexity. Initial estimate should follow: exponential (1,2,4,8,...) OR fibonacci (1,2,3,5,8,...)
Note on C2: How important is this?
Note on D2: Who gets choked if this item doesn't get done?
Note on E2: Done? Blocked? Choose an item from the drop-down menu.

## Sprint 1 Burndown
Sprint 1 Burndown Chart
Date | 3/14 - 3/20 |  |  | 3/21 - 3/27 |  |  | 3/28 - 4/3
Day | W | F | M | W | F | M | W | F | M
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Actual | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
Ideal | 50 | 44 | 38 | 31 | 25 | 19 | 13 | 6 | 0